## Sheet1
| MVP? | PROGRESS | MVP Progress | Notes |  | Done | Started | To Do | Total Tasks
* ~~menu size/padding/margin for laptop and phone~~ | P | DONE | DONE |  | All | 10 | 2 | 14 | 26
* ~~resizing of marging of page based on menu size(div.wrapper margin)~~ | P | DONE | DONE |  |  | 38.46% | 7.692% | 53.85% | 100%
* ~~extra size category between laptop and small(probably limit at 768px)~~ | P | DONE | DONE |  | MVP | 9 | 1 | 5 | 15
* ~~english translation of song in different block for small devices~~ | P | DONE | DONE | ** Done! More or less - some final formatting preferences and tweaks required |  | 60% | 6.667% | 33.33% | 100%
* start thinking about where to put soundcloud thing | O | DONE |  | ** Soundcloud had small song limit, we are planning to use google drive
* ~~song of the month functionality~~ | P | DONE | DONE
* ~~Update variables for the two main colours have been added~~ | P | DONE | DONE | ** they are global veriables defined in styles.css
* Add audio to template file | O | To Do
** add link to json file | O | To Do
** add if statements to check if there even is an audio file yet | O | To Do
* formatting for 3 screen sizes - fix the conditions and boundarys |  | Started |  | Touchscreen and non-touchscreen activated
** list of types:
*** touchscreen small-medium portrait | P | DONE | DONE
*** touchscreen small-medium landscape | O | To Do
*** touchscreen big / computers | P | Started | Started | Computer formatting started, tablets not
* menu for smaller devices | P | DONE | DONE
* song layout for phones (use touchscreen as a condition?) | P | DONE | DONE
*Size of button/text in button (pagination and return to top) | P | To Do | To Do
*Text size consistent on mobile devices | P | To Do | To Do
* Location of hamburger menu option in mobiles centered/neater | P | To Do | To Do
*faint lines on mobile menu | O | To Do
*Text/Narrative on home page to welcome people properly | P | To Do | To Do
*Contributions set up | P | To Do | To Do
* song layout for phones - one column | N | To Do
*Professional Looking | N | To Do |  | Look at other websites, read guide about professional looking websites, get picture from claudio/passa/somewhere
*Tag for themes and historical information set up | O | To Do
*Search function on index | O | To Do

## MVP
MVP OUTSTANDING TASKS
*** touchscreen big / computers | P | Started | Started | Computer formatting started, tablets not
*Size of button/text in button (pagination and return to top) | P | To Do | To Do
*Text size consistent on mobile devices | P | To Do | To Do
* Location of hamburger menu option in mobiles centered/neater | P | To Do | To Do
*Text/Narrative on home page to welcome people properly | P | To Do | To Do
*Contributions set up | P | To Do | To Do